## Project Plan
Project Planing
Task Name | Start Date | End Date | Duration | Start Date in Number Form | 42948 | Use this number for the Minimum Bound of the Horizontal Axis to set the beginning of the chart.
Project Identify and Documentation | 2017-08-01 | 2017-09-03 | 34
Project Planing | 2017-09-01 | 2017-09-30 | 30
Project Infrastructure Analysis and Design | 2017-10-01 | 2017-11-29 | 60
Document Quality Control | 2017-11-01 | 2017-11-15 | 15
Development | 2017-11-16 | 2018-03-15 | 120
Infrastructure Dev. | 2017-11-16 | 2017-12-15 | 30
Backend Task 1 : Recommendation Service | 2017-12-16 | 2017-12-27 | 12
Backend Task 2 : Top Rated Service | 2018-01-01 | 2018-01-12 | 12
Backend Task 3 : SignUp, SignIn and Forgot | 2018-01-13 | 2018-01-24 | 12
Backend Task 4 : Add Rating | 2018-01-25 | 2018-02-05 | 12
Backend Task 5 : Account Manage Service | 2018-02-06 | 2018-02-17 | 12
Backend Task 6 : Search Service | 2018-02-18 | 2018-03-01 | 12
Frontend : Movie Home | 2018-03-02 | 2018-03-03 | 2
Frontend : Sign In, Up, Forgot Panel | 2018-03-04 | 2018-03-05 | 2
Frontend : Movie Detail, Rating and Comment | 2018-03-06 | 2018-03-07 | 2
Frontend : Account Management Master Page | 2018-03-08 | 2018-03-09 | 2
SmokeTest : Movie Home | 2018-03-10 | 2018-03-11 | 2
SmokeTest : Movie Detail, Rating and Comment | 2018-03-10 | 2018-03-11 | 2
SmokeTest : Account Management | 2018-03-10 | 2018-03-11 | 2
TestResult Reinforcement | 2018-03-10 | 2018-03-29 | 20
Implement and Deploy UAT | 2018-03-30 | 2018-04-10 | 12
|  |  |  | Key: | Calculated Cell |  | Manual Entry Cell
[5 empty] | These cells will be automatically calculated based on the inputs on other cells. |  | These cells require manual input so the calculated cells have data to work with.